## Sheet1
Project Plan
Activities | No.Of Weeks | Plan/ Actual | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3
Problem Identification and Literature Survey | 6W | Plan | bar: October 1 to November 2
Actual | bar: October 2 to November 3
Software Requirements and Specifications | 3W | Plan | bar: November 3 to December 1
Actual | bar: November 4 to December 1
Architecture, Design and Prototype | 4W | Plan | bar: December 2 to January 1
Actual | bar: December 2 to December 4
Implementation | 10W | Plan | bar: February 4 to May 1
Actual | bar: February 4 to May 2
Testing and Validation | 3W | Plan | bar: May 2 to May 4
Actual | bar: May 3 to May 4
Project Closure - Results Observations -Demonstration -Report Writing | 3W | Plan | bar: June 1 to June 3
Actual | bar: June 1 to June 3
PLAN
ACTUAL